## Sheet1
Detailed costings for construction project
Location | Description | Work/cost breakdown | Trades | Number of personnel | Total hours | Rate p/h ($) | Total labour | Materials | Equipment | Builders margin | Amount | GST | Total
Site establishment | Preliminaries and site setup | Temporary fencing, amenities, set-out and safety controls | Builder/Labour crew | 3 | 60 | 85 |  | 2500 | 2200 | 2800
Site preparation | Site clearing and stripping | Clear vegetation, strip topsoil and remove spoil | Excavator operator/Labourer | 3 | 56 | 95 |  | 4200 | 4500 | 2500
Earthworks | Site cut and fill works | Cut/fill to design levels and compact in layers to AS2870 requirements | Earthworks contractor | 4 | 90 | 105 |  | 7000 | 8500 | 4200
Substructure | Screw-in piles installation | Install blue/red/green piles to engineering loads and certify | Piling contractor | 3 | 64 | 120 |  | 22000 | 6000 | 6400
Substructure | Suspended waffle raft slab | Excavation prep, reinforcement, concrete placement and finishing | Concreter/Steel fixer | 5 | 140 | 110 |  | 32000 | 11000 | 9800
Substructure | Under-slab services | Sewer/stormwater penetrations and service sleeves before pour | Plumber | 2 | 36 | 100 |  | 3800 | 1400 | 1300
Drainage | Perimeter ag drains and silt pits | Install ag drains, pits and legal discharge connections | Drainage crew | 3 | 52 | 100 |  | 7600 | 2600 | 2500
Retaining walls | Boundary retaining wall works | Construct engineered sleeper/concrete retaining walls and posts | Retaining wall contractor | 4 | 110 | 110 |  | 26000 | 8000 | 7600
Framing | Wall and roof framing | Timber framing package including trusses and bracing | Carpenter | 4 | 180 | 95 |  | 46000 | 3200 | 13300
Roofing | Roof covering, gutters and downpipes | Install roof sheeting/tiles and Colorbond rainwater goods | Roofer | 3 | 90 | 100 |  | 26000 | 2200 | 7900
External envelope | Windows and external doors | Supply/install aluminium windows and external doors | Window/Door installer | 3 | 72 | 95 |  | 29000 | 1300 | 8900
Masonry | External brickwork/render elements | Construct facade brickwork and render features | Bricklayer/Renderer | 4 | 120 | 100 |  | 36000 | 2100 | 11100
Plumbing | Rough-in and fit-off plumbing | Water, gas, sanitary fixtures and rainwater tank connections | Plumber | 3 | 96 | 105 |  | 22000 | 1800 | 6800
Electrical | Electrical rough-in and fit-off | Lighting, power, switchboard, smoke alarms and commissioning | Electrician | 3 | 100 | 110 |  | 16000 | 2400 | 5900
HVAC | Heating/cooling installation | Ducted heating and split system installation | HVAC contractor | 2 | 52 | 120 |  | 9500 | 1600 | 3200
Internal linings | Plasterboard and insulation | Install wall/ceiling linings, insulation and set joints | Plasterer | 4 | 100 | 90 |  | 13000 | 900 | 3900
Internal finishes | Waterproofing and tiling | Wet area membranes and floor/wall tiles to bathrooms/laundry | Waterproofer/Tiler | 3 | 88 | 95 |  | 15000 | 1000 | 4700
Joinery | Kitchen, vanities and laundry joinery | Supply/install cabinetry, stone tops and hardware | Cabinetmaker | 3 | 76 | 95 |  | 28000 | 1200 | 8400
Painting | Internal and external painting | Prime and paint all internal/external painted surfaces | Painter | 3 | 80 | 85 |  | 7200 | 700 | 2300
Floor finishes | Carpet and laminate flooring | Supply/install carpets and hybrid laminate flooring | Flooring contractor | 2 | 48 | 90 |  | 12000 | 600 | 3200
External works | Driveway and paths | Exposed aggregate driveway and perimeter concrete paving | Concreter | 3 | 72 | 100 |  | 14000 | 2600 | 4500
External works | Fencing and landscaping | Boundary fencing, turfing, planting and irrigation provisions | Landscaper/Fencer | 3 | 64 | 90 |  | 12000 | 1400 | 3600
Compliance | Permits, inspections and certification | Permit fees, engineering reviews, occupancy documentation | Project manager/Consultants | 1 | 32 | 140 |  | 5500 | 0 | 1500
Contingency | Construction contingency allowance | Allowance for latent site conditions and market volatility | Contingency | 0 | 0 | 0 |  | 25000 | 0 | 0
Subtotal (ex GST)
GST (10%)
TOTAL ESTIMATED PROJECT COST (incl GST)