Subcontractor Labour Requirements Chart

Enter the types of subcontractors (trades) required and the number required for each month.

| Subcontractor Requirements | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Site establishment / preliminaries | 1 |  |  |  |  |  |  |  |  |  |  |  |
| Demolition / strip-out | 1 |  |  |  |  |  |  |  |  |  |  |  |
| Earthworks / excavation | 1 |  |  |  |  |  |  |  |  |  |  |  |
| Concrete / slab & footings |  | 1 |  |  |  |  |  |  |  |  |  |  |
| Carpentry / framing & fix |  | 1 | 1 |  | 1 | 1 |  |  |  |  |  |  |
| Partitions / linings (wall/ceiling) |  |  | 1 | 1 |  |  |  |  |  |  |  |  |
| Vinyl flooring & wall vinyl installer |  |  |  | 1 | 1 |  |  |  |  |  |  |  |
| Waterproofing (wet areas) |  |  |  | 1 |  |  |  |  |  |  |  |  |
| Plumbing (rough-in + fit-off) |  | 1 | 1 |  | 1 | 1 |  |  |  |  |  |  |
| Electrical (rough-in + fit-off) |  | 1 | 1 |  | 1 | 1 |  |  |  |  |  |  |
| Mechanical / ventilation (exhaust fan) |  |  |  |  | 1 |  |  |  |  |  |  |  |
| Specialist accessibility fitout (grab rails, benches) |  |  |  |  | 1 |  |  |  |  |  |  |  |
| Ceiling hoist installer (Changing Places) |  |  |  |  | 1 |  |  |  |  |  |  |  |
| Painting |  |  |  | 1 | 1 |  |  |  |  |  |  |  |
| Final clean / defects |  |  |  |  |  | 1 |  |  |  |  |  |  |
| Total | 3 | 4 | 4 | 4 | 8 | 4 |  |  |  |  |  |  |