Subcontractor Management Plan

Purpose This subcontractor management plan documents how subcontractors will be selected, organised, and managed for the Well St Brighton WC Upgrade / Adult Changing Facility project. It is used to: - manage and prioritise subcontractor engagement to match the work sequence and workload - confirm each trade's scope, interfaces, and quality/inspection requirements - confirm WHS/OHS expectations (inductions, SWMS, compliance with site rules and legal requirements) - set communication and reporting routines (site meetings, look-ahead planning, progress updates) - reduce risks to cost, time, quality, and safety through clear responsibilities Work sequencing basis (high level): site setup/strip-out -> earthworks -> concrete -> framing/partitions/linings -> rough-ins (plumbing/electrical) -> finishes (vinyl/wall finishes/paint) -> fit-off (sanitaryware/accessories/hoist) -> testing, defects and handover. Labour chart basis: the labour chart numbers represent the number of subcontract trade crews/companies engaged per month (adjust to suit your final program).

Contractor organisational chart Client / Superintendent (Council) -> Principal Contractor (You) -> Site Supervisor / Foreman -> Contract Administrator (procurement, variations, payments) -> HSE / QA support (may be combined role on small projects) -> Subcontractors (trade packages): - Site establishment / preliminaries - Demolition / strip-out - Earthworks / excavation - Concrete - Carpentry / partitions / linings - Waterproofing - Vinyl flooring & wall vinyl - Plumbing - Electrical / lighting / exit signs - Mechanical ventilation (exhaust fan) - Accessibility fitout (grab rails, benches, signage, accessories) - Ceiling hoist installer (Changing Places) - Painting - Final clean / defects

| Roles, rights, responsibilities, and competencies List the subcontractor labour requirements, their relevant roles and responsibilities and competency requirements |  |  |
| --- | --- | --- |
| Subcontractor | Roles, rights, and responsibilities | Competency requirements |
| Site establishment / preliminaries | Responsibilities: provide temporary fencing/signage/amenities as required, set up safe access/egress, establish waste and delivery areas, maintain site security and housekeeping. Rights: confirmed site rules, access times and locations for temporary works. | Competencies: experience on similar council/public sites, ability to maintain compliant site setup, insured. |
| Demolition / strip-out | Responsibilities: isolate/confirm services before demo, remove nominated fixtures/linings, protect retained items, waste separation and lawful disposal, keep site tidy, provide SWMS and competent supervision. Rights: clear demo scope/drawings, confirmed access and shutdowns, agreed hours and waste locations. | Competencies: demonstrated demo experience on similar amenities, relevant licences/tickets, asbestos awareness (if applicable), insured, SWMS/JSA capability. |
| Earthworks / excavation | Responsibilities: set-out support, excavation to levels, manage spoil, protect existing services/structures, temporary shoring/battering as required, reinstate safe access. Rights: DBYD/service info, set-out details, spoil stockpile/haulage instructions. | Competencies: plant operator tickets, experience working near services, ability to document levels and inspections, insured. |
| Concrete (footings/slab) | Responsibilities: formwork/rebar placement, pre-pour inspections, concrete placement/finish, curing/protection, coordinate penetrations with services, provide QA records. Rights: approved drawings, hold point sign-offs, timely access for pre-pour. | Competencies: concreting crew with similar work history, understanding of reinforcement/cover requirements, QA/hold-point compliance, insured. |
| Carpentry / partitions / framing | Responsibilities: framing, noggings, fixings, door framing/hardware backing, coordinate with services, maintain tolerances for finishes and accessibility. Rights: clear shop drawing approvals (if any), confirmed set-out, access to details/schedules. | Competencies: qualified carpenter, experience in wet-area and public amenity construction, ability to coordinate multiple trades, insured. |
| Linings (wall/ceiling) | Responsibilities: install wall/ceiling linings per spec (wet area/impact where required), set-outs for fittings, fire/acoustic requirements if specified, surface prep for finishes. Rights: approved lining types, fixture locations, coordination time with rough-ins. | Competencies: experienced lining contractor, understands wet area requirements, QA sign-off process, insured. |
| Waterproofing | Responsibilities: prepare substrates, apply compliant membrane systems, protect works, arrange required inspections/testing, provide warranty and compliance documentation. Rights: clear substrate readiness sign-off, access to wet-area details. | Competencies: qualified/experienced waterproofer, compliance documentation, proven track record, insured. |
| Vinyl flooring & wall vinyl | Responsibilities: install sheet vinyl and wall vinyl per manufacturer instructions, weld seams, cove upturns where required, ensure slip/trip safety and flush transitions, protect finished surfaces. Rights: confirmed patterns/layouts, substrate moisture readiness. | Competencies: specialist vinyl installer, experience in healthcare/amenities style finishes, manufacturer accreditation (preferred), insured. |
| Plumbing (rough-in + fit-off) | Responsibilities: drainage and water services, install sanitaryware (SS WC/basin), shower fittings, test and commission, certify works, coordinate penetrations and set-outs. Rights: access to fixture schedules and set-out dimensions, timely coordination with walls/linings. | Competencies: licensed plumber, experience with accessible amenities, test/commission capability, insured. |
| Electrical (rough-in + fit-off) | Responsibilities: lighting and power rough-in, install exit lighting/signage as specified, connect hand dryer and exhaust fan, test and certify, provide as-built info. Rights: approved lighting/layout info, access windows before linings. | Competencies: licensed electrician, compliance to AS/NZS 3000 and applicable standards, test equipment, insured. |
| Mechanical ventilation (exhaust fan) | Responsibilities: supply/install exhaust fan (and ducting/penetrations if required), coordinate with electrical, test operation. Rights: approved model/spec and penetration locations. | Competencies: mechanical/ventilation contractor experience, commissioning capability, insured. |
| Accessibility fitout (grab rails/benches/accessories) | Responsibilities: install grab rails, nursing bench/change table, mirrors, dispensers, signage and accessories to drawings and AS1428 requirements, ensure fixings/backing are adequate, provide warranties. Rights: confirmed set-outs and backing requirements before linings close. | Competencies: proven experience with compliant accessible fitouts (AS1428), careful finishing, insured. |
| Ceiling hoist installer (Changing Places) | Responsibilities: install ceiling hoist and track system, coordinate structural fixings and electrical requirements, load test/commission, provide certification and handover training (if required). Rights: approved shop details and fixing points. | Competencies: manufacturer-accredited installer, commissioning and certification capability, insured. |
| Painting | Responsibilities: prepare surfaces, apply specified low VOC/anti-mould systems in wet areas, protect adjacent finishes, complete touch-ups during defects. Rights: approved colour schedule and access after major installs. | Competencies: commercial painter, experience in wet areas, insured. |
| Final clean / defects | Responsibilities: builder's clean, remove stickers/protection as directed, waste removal, assist with defects close-out and handover presentation. Rights: access at completion and clear acceptance criteria. | Competencies: experienced construction cleaner, insured. |

Procedure for managing subcontractors

Consider: - Communicating with the prime contractor - Progress reporting - Review practices and progress reviews - Contract issue meetings - Milestone reviews

1) Procurement & engagement - Confirm scope from drawings/specs and issue RFQ with program dates, site constraints, and quality hold points. - Prequalify: licences, insurances, references, capacity, WHS systems, and ability to meet program. - Award subcontract with clear scope inclusions/exclusions, variation process, and deliverables. 2) Site entry & safety - Mandatory induction, SWMS/JSA review, permits (if required), and verification of competencies. - Daily coordination of high-risk activities; toolbox talks as needed. 3) Communication & reporting - Weekly site meeting + weekly look-ahead plan; daily supervisor check-ins during critical stages. - RFI process for clarifications; written instructions for changes/variations. 4) Quality control - Inspections/hold points (examples): pre-pour, rough-in complete, waterproofing inspection, finishes QA, fit-off checks, commissioning. - Defect management: record, assign owner, re-inspect and close. 5) Progress & payment - Progress claims supported by agreed milestones and evidence; confirm WHS/QA documents supplied prior to payment. 6) Completion & handover - As-builts, warranties, certificates, commissioning results; final clean and practical completion support.

Operational profiles (complete for each subcontractor you select)

For each subcontractor/trade, document:
- Subcontractor business name + primary contact
- Areas of expertise (what they do best)
- Previous performance (recent projects/references; on-time, quality, safety)
- Strengths (e.g., high quality finish, good communication, strong supervision)
- Weaknesses/risks (e.g., resourcing constraints, paperwork delays)
- Controls (how you will manage the weaknesses: increased supervision, hold points, staged deliveries, etc.)